## Detailed Steps
Ticket ID | Epic | Ticket / Task | Step # | Detailed implementation step | Effort (hours) | Effort (days) | Status | Evidence / notes
VCCI-AI-01 | VCCI Desktop | Develop Java Swing AI Chatbot client | 1 | Create Swing window and layout | 4 | 0.5 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-01 | VCCI Desktop | Develop Java Swing AI Chatbot client | 2 | Build prompt and response panels | 6 | 0.75 | Implemented / verify acceptance
VCCI-AI-01 | VCCI Desktop | Develop Java Swing AI Chatbot client | 3 | Connect chatbot to VCCI launcher | 4 | 0.5 | Implemented / verify acceptance
VCCI-AI-01 | VCCI Desktop | Develop Java Swing AI Chatbot client | 4 | Implement background message dispatch | 6 | 0.75 | Implemented / verify acceptance
VCCI-AI-01 | VCCI Desktop | Develop Java Swing AI Chatbot client | 5 | Test launch and response display | 4 | 0.5 | Implemented / verify acceptance
VCCI-AI-02 | VCCI Desktop | Implement agent selection and chat controls | 1 | Populate dropdown with agent entries | 3 | 0.375 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-02 | VCCI Desktop | Implement agent selection and chat controls | 2 | Add AUTO and manual selection behavior | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-02 | VCCI Desktop | Implement agent selection and chat controls | 3 | Wire Refresh and New Chat actions | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-02 | VCCI Desktop | Implement agent selection and chat controls | 4 | Wire Send and Close actions | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-02 | VCCI Desktop | Implement agent selection and chat controls | 5 | Test button behavior and state | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-03 | VCCI Desktop | Display dynamic friendly agent names | 1 | Read friendly names from discovery metadata | 2 | 0.25 | Implemented / verify acceptance | VCCI a52acac
VCCI-AI-03 | VCCI Desktop | Display dynamic friendly agent names | 2 | Preserve internal agent IDs separately | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-03 | VCCI Desktop | Display dynamic friendly agent names | 3 | Update AgentInfo and dropdown renderer | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-03 | VCCI Desktop | Display dynamic friendly agent names | 4 | Verify refresh and renamed agents | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-04 | VCCI Desktop | Implement conversation context and session tracking | 1 | Generate UUID contextId | 2 | 0.25 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-04 | VCCI Desktop | Implement conversation context and session tracking | 2 | Track previousAgentId and lastAutoSelectedAgent | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-04 | VCCI Desktop | Implement conversation context and session tracking | 3 | Preserve context across messages | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-04 | VCCI Desktop | Implement conversation context and session tracking | 4 | Reset context for New Chat | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-04 | VCCI Desktop | Implement conversation context and session tracking | 5 | Test switching agents and sessions | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-05 | VCCI Desktop | Implement response and status handling | 1 | Show outgoing prompt and pending status | 2 | 0.25 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-05 | VCCI Desktop | Implement response and status handling | 2 | Render successful responses | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-05 | VCCI Desktop | Implement response and status handling | 3 | Handle timeouts and connection errors | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-05 | VCCI Desktop | Implement response and status handling | 4 | Test UI responsiveness | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-06 | AI Core Discovery | Integrate VCCI with AI Core agent discovery | 1 | Inspect AI Core discovery contract | 3 | 0.375 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-06 | AI Core Discovery | Integrate VCCI with AI Core agent discovery | 2 | Connect AIService and VCCIControlPanel | 4 | 0.5 | Implemented / verify acceptance
VCCI-AI-06 | AI Core Discovery | Integrate VCCI with AI Core agent discovery | 3 | Map identifiers, commands, and metadata | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-06 | AI Core Discovery | Integrate VCCI with AI Core agent discovery | 4 | Populate chatbot agent list | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-06 | AI Core Discovery | Integrate VCCI with AI Core agent discovery | 5 | Test single and multiple agent discovery | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-07 | AI Core Discovery | Extend GetCommandsRequest with endpoint mappings | 1 | Review existing command data structure | 1 | 0.125 | Implemented / verify acceptance | AI Core bba708e1
VCCI-AI-07 | AI Core Discovery | Extend GetCommandsRequest with endpoint mappings | 2 | Add jAgentURLs map | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-07 | AI Core Discovery | Extend GetCommandsRequest with endpoint mappings | 3 | Implement setter and getter | 1 | 0.125 | Implemented / verify acceptance
VCCI-AI-07 | AI Core Discovery | Extend GetCommandsRequest with endpoint mappings | 4 | Populate mapping from discovery | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-07 | AI Core Discovery | Extend GetCommandsRequest with endpoint mappings | 5 | Verify serialized/received values | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-08 | AI Core Discovery | Cache AI Service agents and endpoint URLs | 1 | Add agent and URL caches | 2 | 0.25 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-08 | AI Core Discovery | Cache AI Service agents and endpoint URLs | 2 | Populate from AI Core responses | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-08 | AI Core Discovery | Cache AI Service agents and endpoint URLs | 3 | Refresh cache on demand | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-08 | AI Core Discovery | Cache AI Service agents and endpoint URLs | 4 | Guard against empty or stale entries | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-09 | AI Core Discovery | Implement agent metadata and skill models | 1 | Define AgentInfo fields | 2 | 0.25 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-09 | AI Core Discovery | Implement agent metadata and skill models | 2 | Define AgentSkillInfo capabilities | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-09 | AI Core Discovery | Implement agent metadata and skill models | 3 | Add endpoint/type/friendly-name fields | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-09 | AI Core Discovery | Implement agent metadata and skill models | 4 | Integrate and test model mapping | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-10 | AI Core Discovery | Validate discovery refresh and failure recovery | 1 | Test zero/one/many agents | 2 | 0.25 | Validation required | Planning estimate; not time logged
VCCI-AI-10 | AI Core Discovery | Validate discovery refresh and failure recovery | 2 | Restart services and refresh | 3 | 0.375 | Validation required
VCCI-AI-10 | AI Core Discovery | Validate discovery refresh and failure recovery | 3 | Test stale URL prevention | 3 | 0.375 | Validation required
VCCI-AI-10 | AI Core Discovery | Validate discovery refresh and failure recovery | 4 | Test malformed metadata | 2 | 0.25 | Validation required
VCCI-AI-10 | AI Core Discovery | Validate discovery refresh and failure recovery | 5 | Record results and defects | 2 | 0.25 | Validation required
VCCI-AI-11 | Intelligent Routing | Implement manual routing to discovered endpoints | 1 | Resolve selected internal agent ID | 2 | 0.25 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-11 | Intelligent Routing | Implement manual routing to discovered endpoints | 2 | Look up discovered endpoint URL | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-11 | Intelligent Routing | Implement manual routing to discovered endpoints | 3 | Pass URL to SendMessageClient | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-11 | Intelligent Routing | Implement manual routing to discovered endpoints | 4 | Remove default-endpoint assumption | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-11 | Intelligent Routing | Implement manual routing to discovered endpoints | 5 | Test per-agent dispatch and errors | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-12 | Intelligent Routing | Implement prompt-based automatic agent selection | 1 | Detect AUTO selection and collect agents | 3 | 0.375 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-12 | Intelligent Routing | Implement prompt-based automatic agent selection | 2 | Build router payload with agents field | 4 | 0.5 | Implemented / verify acceptance
VCCI-AI-12 | Intelligent Routing | Implement prompt-based automatic agent selection | 3 | Call /router/select | 4 | 0.5 | Implemented / verify acceptance
VCCI-AI-12 | Intelligent Routing | Implement prompt-based automatic agent selection | 4 | Parse selection, confidence, and reason | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-12 | Intelligent Routing | Implement prompt-based automatic agent selection | 5 | Resolve selected agent endpoint | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-12 | Intelligent Routing | Implement prompt-based automatic agent selection | 6 | Send prompt to selected agent | 4 | 0.5 | Implemented / verify acceptance
VCCI-AI-12 | Intelligent Routing | Implement prompt-based automatic agent selection | 7 | Test translation and dice prompts | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-13 | Intelligent Routing | Develop AgentRouterClient and response models | 1 | Define routing result and exception types | 2 | 0.25 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-13 | Intelligent Routing | Develop AgentRouterClient and response models | 2 | Implement HTTP client and serialization | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-13 | Intelligent Routing | Develop AgentRouterClient and response models | 3 | Parse response and errors | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-13 | Intelligent Routing | Develop AgentRouterClient and response models | 4 | Integrate client with chatbot | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-13 | Intelligent Routing | Develop AgentRouterClient and response models | 5 | Unit test success and failure paths | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-14 | Intelligent Routing | Implement routing confidence and fallback handling | 1 | Specify confidence interpretation | 2 | 0.25 | Validation required | Planning estimate; not time logged
VCCI-AI-14 | Intelligent Routing | Implement routing confidence and fallback handling | 2 | Validate selected agent against registry | 2 | 0.25 | Validation required
VCCI-AI-14 | Intelligent Routing | Implement routing confidence and fallback handling | 3 | Handle missing URLs and low confidence | 3 | 0.375 | Validation required
VCCI-AI-14 | Intelligent Routing | Implement routing confidence and fallback handling | 4 | Design no-match response behavior | 3 | 0.375 | Validation required
VCCI-AI-14 | Intelligent Routing | Implement routing confidence and fallback handling | 5 | Add logs and tests | 2 | 0.25 | Validation required
VCCI-AI-15 | Intelligent Routing | Resolve automatic routing failures | 1 | Reproduce no-suitable-agent failures | 3 | 0.375 | Validation required | Planning estimate; not time logged
VCCI-AI-15 | Intelligent Routing | Resolve automatic routing failures | 2 | Capture payloads and responses | 3 | 0.375 | Validation required
VCCI-AI-15 | Intelligent Routing | Resolve automatic routing failures | 3 | Inspect agent metadata and matching | 3 | 0.375 | Validation required
VCCI-AI-15 | Intelligent Routing | Resolve automatic routing failures | 4 | Correct request/response inconsistencies | 4 | 0.5 | Validation required
VCCI-AI-15 | Intelligent Routing | Resolve automatic routing failures | 5 | Add regression scenarios and retest | 3 | 0.375 | Validation required
VCCI-AI-16 | Python A2A / Cohere | Implement FastAPI discovery and routing endpoints | 1 | Configure FastAPI app and Uvicorn | 3 | 0.375 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-16 | Python A2A / Cohere | Implement FastAPI discovery and routing endpoints | 2 | Implement /agents endpoint | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-16 | Python A2A / Cohere | Implement FastAPI discovery and routing endpoints | 3 | Implement /router/select endpoint | 4 | 0.5 | Implemented / verify acceptance
VCCI-AI-16 | Python A2A / Cohere | Implement FastAPI discovery and routing endpoints | 4 | Define request and response schemas | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-16 | Python A2A / Cohere | Implement FastAPI discovery and routing endpoints | 5 | Test endpoints and error cases | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-17 | Python A2A / Cohere | Implement A2A JSON-RPC message handling | 1 | Configure A2A routes | 3 | 0.375 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-17 | Python A2A / Cohere | Implement A2A JSON-RPC message handling | 2 | Implement JSON-RPC request parsing | 4 | 0.5 | Implemented / verify acceptance
VCCI-AI-17 | Python A2A / Cohere | Implement A2A JSON-RPC message handling | 3 | Support SendStreamingMessage operation | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-17 | Python A2A / Cohere | Implement A2A JSON-RPC message handling | 4 | Connect handler to execution logic | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-17 | Python A2A / Cohere | Implement A2A JSON-RPC message handling | 5 | Test protocol responses and errors | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-18 | Python A2A / Cohere | Develop router, orchestrator, and executor | 1 | Define component responsibilities | 3 | 0.375 | Validation required | Planning estimate; not time logged
VCCI-AI-18 | Python A2A / Cohere | Develop router, orchestrator, and executor | 2 | Implement agent_router logic | 5 | 0.625 | Validation required
VCCI-AI-18 | Python A2A / Cohere | Develop router, orchestrator, and executor | 3 | Implement agent_orchestrator coordination | 5 | 0.625 | Validation required
VCCI-AI-18 | Python A2A / Cohere | Develop router, orchestrator, and executor | 4 | Implement agent_executor dispatch | 5 | 0.625 | Validation required
VCCI-AI-18 | Python A2A / Cohere | Develop router, orchestrator, and executor | 5 | Align shared data models | 3 | 0.375 | Validation required
VCCI-AI-18 | Python A2A / Cohere | Develop router, orchestrator, and executor | 6 | Test cross-component error handling | 3 | 0.375 | Validation required
VCCI-AI-19 | Python A2A / Cohere | Integrate Cohere North LLM | 1 | Externalize North endpoint and credentials | 2 | 0.25 | Validation required | Planning estimate; not time logged
VCCI-AI-19 | Python A2A / Cohere | Integrate Cohere North LLM | 2 | Initialize North client | 3 | 0.375 | Validation required
VCCI-AI-19 | Python A2A / Cohere | Integrate Cohere North LLM | 3 | Define LLM routing/execution prompts | 3 | 0.375 | Validation required
VCCI-AI-19 | Python A2A / Cohere | Integrate Cohere North LLM | 4 | Parse and validate model output | 3 | 0.375 | Validation required
VCCI-AI-19 | Python A2A / Cohere | Integrate Cohere North LLM | 5 | Handle API errors and timeouts | 2 | 0.25 | Validation required
VCCI-AI-19 | Python A2A / Cohere | Integrate Cohere North LLM | 6 | Run integration tests | 3 | 0.375 | Validation required
VCCI-AI-20 | Python A2A / Cohere | Validate multi-agent interoperability | 1 | Verify discovered endpoints and skills | 2 | 0.25 | Validation required | Planning estimate; not time logged
VCCI-AI-20 | Python A2A / Cohere | Validate multi-agent interoperability | 2 | Test translation and dice agents | 3 | 0.375 | Validation required
VCCI-AI-20 | Python A2A / Cohere | Validate multi-agent interoperability | 3 | Test speech/social/structured-text/database agents | 4 | 0.5 | Validation required
VCCI-AI-20 | Python A2A / Cohere | Validate multi-agent interoperability | 4 | Test manual versus AUTO flows | 3 | 0.375 | Validation required
VCCI-AI-20 | Python A2A / Cohere | Validate multi-agent interoperability | 5 | Test unavailable agent behavior | 2 | 0.25 | Validation required
VCCI-AI-20 | Python A2A / Cohere | Validate multi-agent interoperability | 6 | Document results | 2 | 0.25 | Validation required
VCCI-AI-21 | Build / Runtime | Externalize AI routing configuration | 1 | Add ROUTER_URL to application.yml | 1 | 0.125 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-21 | Build / Runtime | Externalize AI routing configuration | 2 | Load configuration in Java client | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-21 | Build / Runtime | Externalize AI routing configuration | 3 | Test invalid and changed endpoints | 1 | 0.125 | Implemented / verify acceptance
VCCI-AI-22 | Build / Runtime | Resolve Micronaut bean discovery and startup | 1 | Reproduce missing bean error | 2 | 0.25 | Implemented / verify acceptance | Planning estimate; not time logged
VCCI-AI-22 | Build / Runtime | Resolve Micronaut bean discovery and startup | 2 | Check source location and module | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-22 | Build / Runtime | Resolve Micronaut bean discovery and startup | 3 | Inspect generated bean definitions | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-22 | Build / Runtime | Resolve Micronaut bean discovery and startup | 4 | Resolve wiring without legacy JDBC changes | 3 | 0.375 | Implemented / verify acceptance
VCCI-AI-22 | Build / Runtime | Resolve Micronaut bean discovery and startup | 5 | Clean build and startup test | 2 | 0.25 | Implemented / verify acceptance
VCCI-AI-23 | Build / Runtime | Validate Maven builds and runtime dependencies | 1 | Confirm JDK and Maven configuration | 2 | 0.25 | Validation required | Planning estimate; not time logged
VCCI-AI-23 | Build / Runtime | Validate Maven builds and runtime dependencies | 2 | Review private dependencies | 2 | 0.25 | Validation required
VCCI-AI-23 | Build / Runtime | Validate Maven builds and runtime dependencies | 3 | Run clean builds | 3 | 0.375 | Validation required
VCCI-AI-23 | Build / Runtime | Validate Maven builds and runtime dependencies | 4 | Investigate GitLab pipeline failures | 3 | 0.375 | Validation required
VCCI-AI-23 | Build / Runtime | Validate Maven builds and runtime dependencies | 5 | Document reproducible startup | 2 | 0.25 | Validation required
VCCI-AI-24 | Delivery / Testing | Recover and commit integration changes | 1 | Review VCCI stash and working tree | 2 | 0.25 | Validation required | Recovery branch 92dd879; verify differences
VCCI-AI-24 | Delivery / Testing | Recover and commit integration changes | 2 | Commit and push VCCI feature branch | 2 | 0.25 | Validation required
VCCI-AI-24 | Delivery / Testing | Recover and commit integration changes | 3 | Compare AI Core recovery and target branches | 3 | 0.375 | Validation required
VCCI-AI-24 | Delivery / Testing | Recover and commit integration changes | 4 | Transfer only approved missing changes | 3 | 0.375 | Validation required
VCCI-AI-24 | Delivery / Testing | Recover and commit integration changes | 5 | Verify remote hashes and unchanged master | 2 | 0.25 | Validation required
VCCI-AI-25 | Delivery / Testing | Integration tests, documentation, and release evidence | 1 | Document architecture and API contracts | 3 | 0.375 | Validation required | Planning estimate; not time logged
VCCI-AI-25 | Delivery / Testing | Integration tests, documentation, and release evidence | 2 | Write discovery and routing test cases | 4 | 0.5 | Validation required
VCCI-AI-25 | Delivery / Testing | Integration tests, documentation, and release evidence | 3 | Execute end-to-end tests | 4 | 0.5 | Validation required
VCCI-AI-25 | Delivery / Testing | Integration tests, documentation, and release evidence | 4 | Capture logs and CI evidence | 3 | 0.375 | Validation required
VCCI-AI-25 | Delivery / Testing | Integration tests, documentation, and release evidence | 5 | Document defects and release readiness | 2 | 0.25 | Validation required

## Ticket Summary
Ticket ID | Epic | Ticket / Task | Total hours | Total days | Status | Step count | Detail source range
VCCI-AI-01 | VCCI Desktop | Develop Java Swing AI Chatbot client | 24 | 3 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F2:F6
VCCI-AI-02 | VCCI Desktop | Implement agent selection and chat controls | 12 | 1.5 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F7:F11
VCCI-AI-03 | VCCI Desktop | Display dynamic friendly agent names | 8 | 1 | Implemented / verify acceptance | 4 | 'Detailed Steps'!F12:F15
VCCI-AI-04 | VCCI Desktop | Implement conversation context and session tracking | 12 | 1.5 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F16:F20
VCCI-AI-05 | VCCI Desktop | Implement response and status handling | 8 | 1 | Implemented / verify acceptance | 4 | 'Detailed Steps'!F21:F24
VCCI-AI-06 | AI Core Discovery | Integrate VCCI with AI Core agent discovery | 16 | 2 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F25:F29
VCCI-AI-07 | AI Core Discovery | Extend GetCommandsRequest with endpoint mappings | 8 | 1 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F30:F34
VCCI-AI-08 | AI Core Discovery | Cache AI Service agents and endpoint URLs | 8 | 1 | Implemented / verify acceptance | 4 | 'Detailed Steps'!F35:F38
VCCI-AI-09 | AI Core Discovery | Implement agent metadata and skill models | 8 | 1 | Implemented / verify acceptance | 4 | 'Detailed Steps'!F39:F42
VCCI-AI-10 | AI Core Discovery | Validate discovery refresh and failure recovery | 12 | 1.5 | Validation required | 5 | 'Detailed Steps'!F43:F47
VCCI-AI-11 | Intelligent Routing | Implement manual routing to discovered endpoints | 12 | 1.5 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F48:F52
VCCI-AI-12 | Intelligent Routing | Implement prompt-based automatic agent selection | 24 | 3 | Implemented / verify acceptance | 7 | 'Detailed Steps'!F53:F59
VCCI-AI-13 | Intelligent Routing | Develop AgentRouterClient and response models | 12 | 1.5 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F60:F64
VCCI-AI-14 | Intelligent Routing | Implement routing confidence and fallback handling | 12 | 1.5 | Validation required | 5 | 'Detailed Steps'!F65:F69
VCCI-AI-15 | Intelligent Routing | Resolve automatic routing failures | 16 | 2 | Validation required | 5 | 'Detailed Steps'!F70:F74
VCCI-AI-16 | Python A2A / Cohere | Implement FastAPI discovery and routing endpoints | 16 | 2 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F75:F79
VCCI-AI-17 | Python A2A / Cohere | Implement A2A JSON-RPC message handling | 16 | 2 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F80:F84
VCCI-AI-18 | Python A2A / Cohere | Develop router, orchestrator, and executor | 24 | 3 | Validation required | 6 | 'Detailed Steps'!F85:F90
VCCI-AI-19 | Python A2A / Cohere | Integrate Cohere North LLM | 16 | 2 | Validation required | 6 | 'Detailed Steps'!F91:F96
VCCI-AI-20 | Python A2A / Cohere | Validate multi-agent interoperability | 16 | 2 | Validation required | 6 | 'Detailed Steps'!F97:F102
VCCI-AI-21 | Build / Runtime | Externalize AI routing configuration | 4 | 0.5 | Implemented / verify acceptance | 3 | 'Detailed Steps'!F103:F105
VCCI-AI-22 | Build / Runtime | Resolve Micronaut bean discovery and startup | 12 | 1.5 | Implemented / verify acceptance | 5 | 'Detailed Steps'!F106:F110
VCCI-AI-23 | Build / Runtime | Validate Maven builds and runtime dependencies | 12 | 1.5 | Validation required | 5 | 'Detailed Steps'!F111:F115
VCCI-AI-24 | Delivery / Testing | Recover and commit integration changes | 12 | 1.5 | Validation required | 5 | 'Detailed Steps'!F116:F120
VCCI-AI-25 | Delivery / Testing | Integration tests, documentation, and release evidence | 16 | 2 | Validation required | 5 | 'Detailed Steps'!F121:F125
TOTAL |  |  | 336 | 42

## Epic Summary
Epic | Ticket count | Estimated hours | Estimated days
VCCI Desktop | 5 | 64 | 8
AI Core Discovery | 5 | 52 | 6.5
Intelligent Routing | 5 | 76 | 9.5
Python A2A / Cohere | 5 | 88 | 11
Build / Runtime | 3 | 28 | 3.5
Delivery / Testing | 2 | 28 | 3.5
TOTAL | 25 | 336 | 42
Planning assumptions | Value
Hours per day | 8
Contingency low | 15%
Contingency high | 20%
Total with 15% contingency (hours) | 386.4
Total with 20% contingency (hours) | 403.2

## Read Me
VCCI–Cohere AI Integration — Effort Planning
Workbook purpose | Retrospective planning estimates with per-step breakdown for 25 proposed GitLab tickets.
Detailed Steps | One row per implementation step, with estimated hours and calculated days.
Ticket Summary | One row per GitLab ticket; total effort calculated from Detailed Steps.
Epic Summary | Formula-driven epic totals, contingency assumptions, and chart.
Estimate basis | 1 developer-day = 8 hours; estimates are not actual time worked.
Status caveat | Implemented indicates prior demonstration; verify acceptance and CI before closure.
Scope | Java Swing VCCI, AI Core Micronaut, FastAPI/A2A, Cohere North, routing, Git recovery.